Oliver Samuels

3/18/22

CS 411

1. When is the project estimated to be completed? How long will the project take to complete?

The project is estimated to complete 11/18/22 if started 3/18/22 for a total of 176 days

1. What is the critical path for the project? List the activity names.

The critical path is all activities apart from task 3 which is product design so its actually

Mark analysis, Requirements’ analysis, Design selection, detailed design, implementation process, testing product, Install Bluestone ins a car, do acceptance testing, and celebrate

1. List the activity names with floating time? Identify the float time for each of such activities.

The activities with floating time are Install Bluestone in a car and the floating time is the entirety of the Testing Product time from September 2nd to September 22nd or 20 days

1. After reviewing the initial project plan, the duration of both the “Implementation process” and “Testing product” tasks have been updated and become 35 days and 17 days, respectively. Now, how long will the project take to complete? When is the project estimated to be completed

The project is estimated to complete on 11/29/22 if started 3/18/22 for a total of 183 days